## Shopenzer Testcases
|  |  |  | Date | 2022-11-17
|  |  |  | Team ID | PNT2022TMID24001
|  |  |  | Project Name | Inventory Management Systems for Retailers
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
LoginPage_1 | Functional | Home Page | Make sure the user can view the Login/Signup box after clicking the Get Started or Sign Up button. | 1.Enter the url and page will be directed 2.Make sure you can able to see login/register page |  | The login page should appear. | Working | Pass | Working | Y |  | Mohamed Yaseen
LoginPage_2 | Functional | Home Page | Check to see if the user can access the application using valid credentials. | 1.Enter username/email in Email text box 2.Enter password in password text box 3.Enter with valid credentials 4.Click on login button | Username: test Password: 123456 | The user should go to the dashboard. | Working | Pass | Working | Y |  | Mohamed Yaseen
LoginPage_3 | Functional | Login page | Check if the user can access the application with invalid credentials. | 1.Enter invalid username text box 2.Enter valid password in password text box 3.Click on login button | Username: test123 Password: testing123 | Application should show 'Invalid Login Credentials' | Working | Pass | Working | Y |  | Mohamed Aswerdeen M
LoginPage_4 | Functional | Login page | Check if the user can access the application with invalid password. | 1.Enter valid username/email in Email text box 2.Enter invalid password in password text box 3.Click on login button | Username: test password: test132 | Application should show 'Incorrect password ' | Working | Pass | Working | Y |  | Mohamed Aswerdeen M
LoginPage_5 | Functional | Login page | Check to see if the user can access the programme without an email | 1.Leave the email text box as empty 2.Enter password in password text box 3.Click on login button | Username: password: rass | Please enter your username | Working | Pass | Working | Y |  | Mohamed Aswerdeen M
LoginPage_6 | Functional | Login page | Check to see if the user can access the programme without a password | 1.Enter username/email in Email text box 2.Leave the password text box as empty 3.Click on Login Button | Username: rass password: | Please enter your password | Working | Pass | Working | Y |  | Mohamed Aswerdeen M
Dashboard_1 | Functional | Dashboard | Create a dashboard | 1.Place the catalogue in the dashboard upon categories 2.Shops, location and products should be shown 3. Click the desired product and order |  | Dashboard should be displayed | Working | Pass | Working | N |  | Abdur Rahman M Y
Dashboard_2 | Functional | Dashboard | Display the shops of which catalogue is known for | 1.Log on to the application 2.Go to dashboard 3.Go to shops 4.Add shops and status |  | Shops will be displayed along with their status | Working | Pass | Working | N |  | Abdur Rahman M Y
Dashboard_3 | Functional | Dashboard | Display the location of which catalogue is known for | 1.Login to application 2.Go to dashboard 3.Go to location 4.Create the location of product |  | Location and their details will be shown | Working | Pass | Working | N |  | Abdur Rahman M Y
Dashboard_4 | Functional | Dashboard | Display the products of which catalogue is known for | 1.Login to application 2.Go to dashboard 3.Go to products 4.Add the products, their quantity and cost |  | Products will be displayed along with their quantity and cost | Working | Pass | Working | N |  | Abdur Rahman M Y
Dashboard_5 | Functional | Dashboard | Create an remove toggle for the products which should be removed | 1.Login to application 2.Go to dashboard 3.Go to which items you want to remove. 4.Click the delete toggle button. |  | Items which is going to be removed should be noticed | Working | Pass | Working | N |  | Mohamed Hassan S
Dashboard_6 | Functional | Dashboard | Viewing the sales growth of frequently selling products | 1.Loin to application 2.Go to Dashboard 3.View the sales analytics |  | Sales growth of frequently selling products should be displayed | Working | Pass | Working | Y |  | Mohamed Hassan S
Database_1 | Functional | Database | Integrate sendgrid and an api key | 1.Register with sendgrid 2.Confirmation with mail 3.API key generation 4.Integrating sendgrid and API |  | Integrating sendgrid and api key with database | Working | Pass | Working | Y |  | Mohamed Yaseen
Database_2 | Functional | Database | Integrate the flask programme with the database as a user. | 1.Create connection between database and flask 2.Store the data with IBM Db2 3.Ensure the data given is updated and working |  | Flask program should be integrated with database IBM Db2 | Working | Pass | Working | Y |  | Mohamed Yaseen
Database_3 | Functional | Database | Integrate the product set with the database | 1.Creating shops, location and product set in table 2.View the data stored |  | Shops, location and product set should be integrated with database | Working | Pass | Working | Y |  | Mohamed Yaseen

## Testscearnios
Test Scenarios
1 | Verify user is able to see login page
2 | Verify user is able to loginto application or not?
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to recovery password
5 | Veriify login page elements
Search
1 | Verify user is able to search by entering keywords in search box
2 | Verify user is able to see suggestions based on keyword entered in search box
3 | Verify user is able to see related auto suggestions displaying based on keyword entered in search box
4 | Verify user is able to see no matches found message when no results are matching with entered keyword
5 | Verify user is able to see seach detailed page when nothing entered in textbox